## Slide 1: MEETING_4&5_15MARCH
Nitin D. Patwari
Anjul Srivastavs

## Slide 2: Work progress
Sr. No. | Date | To Do | Done
1) | 1st JAN to 18th JAN | Go through the papers and decide the feasibility to implement them. | Studied both the papers and overviewed the basic concepts required to understand the paper. Decided to implement paper [1] then [2].
2) | 18th JAN to 1st Feb | Implement Karatsuba multiplier. | Implemented Conventional multiplier. Started implementation of Karatsuba multiplier (completed for operands of the form n=2m).
3) | 1st Feb to 15th Feb | Implement Karatsuba multiplier for n={93, 131, 163, 193, 233, 283, 409} | Done implementation of Karatsuba multiplier for n={93, 131, 163, 193, 233, 283, 409}
1] An Efficient and High Speed Overlap Free Karatsuba Based Finite Field Multiplier for FGPA Implementation.
2] Cryptographic Accelerators for Digital Signature Based on Ed25519.

## Slide 3
Sr. No. | Date | To Do | Done
4) | 15th FEB to 1st MAR | Implementation of OKA and OBS. | Done implementation of OKA and OBS for n={93, 131, 163, 193, 233, 283, 409}
5) | 1st MAR to 15th MAR | Calculate delay and area for implemented algorithms FPGA board | Done implementation and analysis CA, KA, OKA and OBS.

## Slide 4: OKA

## Slide 5: OBS

## Slide 6: How Levels affect area and delay ?

## Slide 7: Work done between 1stMARCH - 15thMARCH

## Slide 8: Area and Delay plots (CA,KA,OKA)

## Slide 9: Area and Delay plots (OBS)
Chart: Delay
| 93 | 131 | 163 | 193 | 233 | 283
 | 9.961 | 12.114 | 12.211 | 14.429 | 16.728 | 16.812
Chart: Area
| 93 | 131 | 163 | 193 | 233 | 283
 | 2501 | 4337 | 6420 | 8396 | 11866 | 20800

## Slide 10: THANK YOU !!